SpyKids — Research Plan

Topic: Left-behind children (parental absence due to labour migration)

Course: DECO2850/DECO7285 Studio 2 — Interaction Design, Semester 2 2026

Phase: Problem Identification (no design/solution specification at this stage)

# 1. Purpose

This research plan exists to ground the team's understanding of the problem space in evidence rather than assumption, before any interaction design work begins. It does not propose a solution — its sole output is a well-evidenced problem framing that will feed Assessment 1 (individual proposal) and the team's ongoing design journal.

# 2. Research Questions

Primary research question: How does parental absence affect left-behind children's emotional wellbeing, guidance, and development — and what is actually needed to address this gap?

Sub-questions to guide data collection:

| # | Sub-question | Maps to framing heading |
| --- | --- | --- |
| RQ1 | Who is affected, directly and indirectly, by a parent's labour migration? | Who |
| RQ2 | What forms does the separation take (duration, distance, communication frequency, caregiving arrangement)? | How |
| RQ3 | What economic, social, or structural factors drive the decision to migrate? | Why |
| RQ4 | What downstream effects are observed on wellbeing, academic outcomes, and family relationships? | Impact |
| RQ5 | Where might the team's assumptions about "left-behind children" as a uniform group break down? | Risks |

# 3. Target Information Sources & Stakeholders

Because direct research contact with children is ethically sensitive and likely outside the scope/timeline of this studio, prioritise indirect and secondary sources first, escalating to direct contact only where appropriate and low-risk.

Assessment 2 sets a hard requirement here: each team member must personally engage at least one participant using a specific method, and the team as a whole should reach 6–10 participants across the study. This isn't optional scoping — it's graded criteria for the Weeks 3–5 milestone.

| Source type | Examples | Priority |
| --- | --- | --- |
| Secondary literature | Peer-reviewed studies on migration and child development, NGO/government reports (e.g. UNICEF, ChildFund) | High — supports but doesn't replace the participant requirement |
| Adults with lived proximity to the issue | Teachers, school counsellors, extended-family caregivers, community workers | High — main source for the 6–10 participant target |
| Online communities | Forums, support groups, social media spaces where migrant parents/caregivers discuss the experience | Medium |
| Object-based/artefact methods | Analysis of existing tools/apps already used by these families (e.g. video call apps, remittance apps) | Medium |
| Peers with relevant personal/family experience | Team members' own networks, only with informed and voluntary participation | Low — sensitive, opt-in only |

# 4. Suite of Methods (per Week 3 studio taxonomy)

Week 3's studio activity was specifically "Develop a Suite of Methods for your project," using the following taxonomy. Rather than a generic method list, the team's actual suite should be built from this set, with one method assigned per team member so everyone independently engages at least one participant (Assessment 2 requirement).

| Method | Type | What it involves | Best fit for this project |
| --- | --- | --- | --- |
| Contextual Inquiry | Ethnography | Combined interview + in-field observation; go in without preconceived assumptions (master/apprentice or partnership mode) | Observing a caregiving household or classroom setting, if access allows |
| Rapid Ethnography | Ethnography | Quicker, focused version — narrow focus, key informants, multiple observers, cooperative analysis | Time-boxed sessions with teachers/community workers given the tight timeline |
| Digital Ethnography | Ethnography | Immersing in an online community, following ethical conduct, informing the gatekeeper, observing/participating | Migrant-parent or caregiver support forums/groups |
| Mapping | Object-based | Ask a participant to draw a map then question them about it | Mapping a family's communication routine across distance |
| Object Inventory | Object-based | Use physical/digital objects in a participant's environment as interview prompts | Communication tools/objects a family already relies on |
| Autoethnography | Reflexive | Team member studies the environment through their own experience, using reflexivity — not a diary | Only if a member has directly relevant lived experience; opt-in, use cautiously |

Suggested method-to-member assignment (fill in with actual names):

| Team member | Assigned method | Target participant(s) |
| --- | --- | --- |
| Member 1 | Contextual Inquiry / Rapid Ethnography | 1+ |
| Member 2 | Digital Ethnography | 1+ (observation-based) |
| Member 3 | Mapping | 1+ |
| Member 4 | Object Inventory | 1+ |
| Member 5 | Contextual/Rapid Ethnography (2nd instance) | 1+ |
| Member 6 | Digital Ethnography or Mapping (2nd instance) | 1+ |

This gives 6+ participants minimum, within the 6–10 range Assessment 2 expects, while covering the method diversity the studio taught.

# 5. Ethical Considerations

Assessment 2 explicitly requires the team to "add ethical insights and principles in your approach" — this needs to be documented evidence, not just an internal team norm.

- No direct research contact with children — all primary data collection is with adults or via secondary/public sources.

- Informed consent for any interview: voluntary participation, right to withdraw at any time.

- Anonymity/confidentiality: no identifying details in journal entries, proposals, or exhibits.

- Digital ethnography conduct: notify the online community/gatekeeper before observing or participating, and understand community norms first.

- Sensitivity: pilot interview questions within the team first; avoid pressing on distressing details.

- Revisit ethics after data collection (per Week 4 studio topic), not just before.

- Document as you go: capture a short ethical-insight note alongside each piece of evidence so the documentation itself satisfies Assessment 2's requirement.

# 6. Data Analysis Approach

- Qualitative thematic analysis (per Week 5 studio topic) on interview notes and ethnography logs.

- Code data against the five framing headings (Who/How/Why/Impact/Risks) plus an "unexpected" category.

- Synthesis session as a team to reconcile findings across methods and update the assumptions list.

# 7. Timeline (aligned to Assessment 2's official Weeks 3–5 process)

| Week | Activity | Output |
| --- | --- | --- |
| Week 3 | Literature review; finalise Suite of Methods and per-member assignment; draft assumptions; begin ethics prep | Annotated bibliography, method-to-member assignment, assumptions list |
| Week 4 | Each member conducts their assigned method with at least one participant; ethics re-check as data comes in | Transcripts/observation logs/maps/inventories — evidence of individual engagement |
| Week 5 | Complete remaining participant engagements (target 6–10 total); qualitative data analysis; team synthesis session | A design concept based on data analysis + updated Who/How/Why/Impact/Risks framing |
| Weeks 6–7 | Design concept feeds into individual Assessment 1 proposals and Iteration 1 prototyping | Individual proposals (07/09/26), early prototype work |
| Week 9 onward | Research resumes in evaluative form (user enactment, field trials) once a prototype exists | Evaluation data (separate from this plan) |

Important nuance: Assessment 2 expects a team-level "design concept" to emerge by the end of Week 5 — earlier than the individual Assessment 1 proposal (due Week 7) might suggest. This isn't a full design specification; it's the point where the team's data analysis should start pointing toward a shared direction, which each member then individually develops in their own Assessment 1 proposal. Keep the Week 5 "concept" at the level of a direction/hypothesis, not a specified solution.

# 8. Limitations & Risks

- Access: the team may have limited direct access to people with first-hand experience; weight secondary sources and online ethnography accordingly.

- Small sample size: interview findings are illustrative, not statistically representative.

- Risk of assuming uniformity: explicitly test that the experience is similar across age groups, geographies, and family structures.

- Emotional sensitivity: be prepared for interviews or ethnography to surface distressing content.

# 9. Deliverables (mapped to Assessment 2 requirements)

- Annotated bibliography

- Interview transcripts / observation logs / maps / object inventories — one piece of evidence per team member, showing individual engagement with at least one participant

- Online/digital ethnography log (with gatekeeper/community notified per ethical conduct expectations)

- Ethical insights and principles documented alongside the data (explicit Assessment 2 requirement)

- A design concept based on data analysis — the formal Week 3–5 output Assessment 2 grades

- Synthesised problem framing (updated Who/How/Why/Impact/Risks doc in Miro)

Feeds directly into Assessment 1, Iteration 1 prototyping, and ongoing design journal entries.