SpyKids — Project Plan (Master Schedule)

Topic: Left-behind children (parental absence due to labour migration) | Course: DECO2850/DECO7285 Studio 2, Sem 2 2026

Research Question: How does parental absence affect left-behind children's emotional wellbeing, guidance, and development — and what is actually needed to address this gap?

Assessments are a by-product, not the goal. This schedule is built around doing the project properly — understanding the problem, gathering real evidence, and iterating with care. Assessment 1, Milestones 1–3, Assessment 3, and Assessment 4 all fall out naturally from that work when it's done well. The team's focus should stay on the work; the submissions take care of themselves.

Method Team Assignments (agreed Week 4):

| Method | Lead | Support |
| --- | --- | --- |
| Literature Review | Charles | Niwel |
| Interview | CJ | Yajie / Niwel |
| Ethnography / Digital | CJ | Anton |
| Questionnaire / Survey | Simon | Niwel |

| Phase | Week | Task | Expected Outcome | Start – Target End | Team Member |
| --- | --- | --- | --- | --- | --- |
| 1 Problem Identification | 2–3 | Clearly identify and frame the problem based on initial ideation process | Draft a Problem Identification Document detailing initial assumptions, Who/How/Why/Impact/Risks framing, and the financial-difficulty segmentation | Start: Week 2 End: Week 3 (Fri) | Whole Team Draft: Niwel |
|  | 3 | Literature scan + method selection for the Suite of Methods | Annotated bibliography (8–10 sources) + method shortlist with rationale | Start: Week 3 End: Week 3 (Fri) | Charles (Lead), Niwel (Support) |
|  | 4 | Pilot selected methods with 1–2 participants; ethics pass | Pilot notes + Ethics Considerations draft | Start: Week 4 End: Week 4 (Fri) | CJ (Lead), Niwel (Support) |
|  | 4 | Finalise and review Problem Identification Document against gate checklist | Reviewable Problem Identification Document with completed Assumptions Register | Start: Week 4 End: Week 4 (Fri) | Whole Team |
| 2 – Knowledge Gathering | 4 | Complete literature review | Fuller annotated bibliography (8–10+ sources) | Start: Week 4 End: Week 4 (Fri) | Charles (Lead), Niwel (Support) |
| 2 – Knowledge Gathering | 4 | Formulate question guides per assigned method | Method-specific question/prompt guides | Start: Week 4 End: Week 4 (Fri) | All Members (per Method Team table) |
| 2 – Knowledge Gathering | 4–5 | Conduct interviews | Interview transcripts | Start: Week 4 End: Week 5 (Fri) | CJ (Lead), Yajie/Niwel (Support) |
| 2 – Knowledge Gathering | 4–5 | Conduct ethnography / digital ethnography | Ethnography / digital ethnography log | Start: Week 4 End: Week 5 (Fri) | CJ (Lead), Anton (Support) |
| 2 – Knowledge Gathering | 4–5 | Conduct questionnaire / survey | Survey response data | Start: Week 4 End: Week 5 (Fri) | Simon (Lead), Niwel (Support) |
| 2 – Knowledge Gathering | 5 | Qualitative data analysis | Coded findings against Who/How/Why/Impact/Risks + segmentation | Start: Week 5 End: Week 5 (Fri) | Whole Team |
| 2 – Knowledge Gathering | 5 | Team synthesis session | Synthesised findings + updated problem framing | Start: Week 5 End: Week 5 (Fri) | Whole Team |
| 2 – Knowledge Gathering | 5 | Draft design concept hypothesis | Design concept hypothesis (a direction, not a spec) | Start: Week 5 End: Week 5 (Fri) | Whole Team |
| 2 – Knowledge Gathering (by-product) | 4–7 | Develop and write up your own perspective on the problem and its solution direction, grounded in the shared Phase 1–2 research | This individual synthesis is submitted as Assessment 1 (~1500 words) | Start: Week 4 End: 07/09 (Mon) | All Members (individually) |
| 3 – Iteration 1 / Exhibit 1 | 6 | Converge on one team direction from proposals + design concept hypothesis | Agreed team direction, documented | Start: Week 6 End: Week 6 (Fri) | Whole Team |
| 3 – Iteration 1 / Exhibit 1 | 6–7 | Sketch and critique concepts | 2–3 concept sketches critiqued, one selected | Start: Week 6 End: Week 7 (Fri) | Whole Team |
| 3 – Iteration 1 / Exhibit 1 | 7–8 | Build and internally test prototype | Low/mid-fidelity interactive prototype | Start: Week 7 End: Week 8 (Fri) | Whole Team |
| 3 – Iteration 1 / Exhibit 1 | 8 | Bring the prototype and process to a state worth showing and getting feedback on | Design Exhibit 1 delivered (Milestone 1), feedback received | Start: Week 8 End: 17/09 | Whole Team |
| 4 – User Enactment & Evaluation | 9 | Design and run user enactment activity | Enactment notes + video/photo evidence | Start: Week 9 End: 24/09 | Whole Team |
| 4 – User Enactment & Evaluation | 9–10 | Analyse enactment findings | Revised prototype backlog | Start: Week 9 End: Week 10 (Fri) | Whole Team |
| 4 – User Enactment & Evaluation | 10 | Plan evaluation approach | Evaluation plan | Start: Week 10 End: 08/10 | Whole Team |
| 4 – User Enactment & Evaluation | 11 | Conduct field trial (2+ rounds if possible) | Field trial data + iteration log | Start: Week 11 End: 15/10 | Whole Team |
| 4 – User Enactment & Evaluation | 11 | Synthesise findings into concrete design changes | Prioritised change list for Phase 5 | Start: Week 11 End: Week 11 (Fri) | Whole Team |
| 5 – Iteration 2 / Exhibit 2 | 12 | Refine prototype using field trial insights | High-fidelity, polished prototype | Start: Week 12 End: 22/10 | Whole Team |
| 5 – Iteration 2 / Exhibit 2 | 13 | Bring the refined prototype and process to a state worth showing and getting feedback on | Design Exhibit 2 delivered (Milestone 2), feedback received | Start: Week 13 End: 29/10 | Whole Team |
| 6 – Wrap-up | 14 | Consolidate the semester's work and reflect on what was learned (SWOT VAC — no scheduled studio) | Report draft in progress | Start: Week 14 End: Week 14 (Fri) | Whole Team |
| 6 – Wrap-up | 15 | Write up the project's process, findings, and outcomes | ~3,000-word Project Report submitted (Milestone 3) | Start: Week 15 End: 13/11 | Whole Team |
| 6 – Wrap-up | 15 | Reflect individually on the semester's design journal and process | Assessment 3 interview completed | Start: Week 15 End: 13/11 | All Members (individually) |
| 6 – Wrap-up | 16 | Critically review the team's interaction design work (PG requirement) | Assessment 4 submitted | Start: Week 16 End: 16/11 | PG Members (individually) |

Notes:

• Assessments follow from the work, not the other way around. Every task above is written as project work first; the assessment/milestone it satisfies is the outcome, not the driver. If a task and an assessment requirement ever seem to pull in different directions, do the work properly and trust that the assessment takes care of itself.

• Assessment 1 is listed under Phase 2 as a by-product, not its own phase — it's an individual deliverable drawn from the shared Phase 1–2 research base, not a gated stage of the project.

• Phase 1 doesn't close until the Problem Identification Document is reviewable and its gate checklist is satisfied — Phase 2 starts from that document.

• Method Team assignments per Week 3 studio outcome. Niwel supports three of the four methods (Literature Review, Interview, Questionnaire/Survey) in addition to authoring the shared documentation — worth keeping an eye on workload balance as Phase 2 progresses.