DECO2850/DECO7285 Studio 2 - Interaction Design

Semester 2 2026

Project Plan

Topic: Left-behind children (parental absence due to labour migration)

Document No: SK-P1-000

Research Question: How does parental absence affect left-behind children's emotional wellbeing, guidance, and development — and what is actually needed to address this gap?

Assessments are a by-product, not the goal. This plan is built around doing the project properly — understanding the problem, gathering real evidence, and iterating with care. Assessment 1, Milestones 1–3, Assessment 3, and Assessment 4 all fall out naturally from that work when it's done well. Keep the team's focus on the work; the submissions take care of themselves.

# Phase 1 — Problem Identification (Current Phase)

Weeks 2–4 (through 20/08/26)

This is where the team is now. No solution or design framing yet — the goal is a rigorous, well-evidenced articulation of the problem space. Rather than one research pass, run this as two short cycles so early findings can reshape what you look at next.

## Week 3 Scoping Outcome (team brainstorm)

The team's Week 3 session already produced a working scope, splitting the problem by financial difficulty status — treating this as a key variable that changes what left-behind children actually need:

| Segment | Sub-problem | Team's early hypothesis |
| --- | --- | --- |
| Without financial difficulty | Time / companionship | No companion present day-to-day |
| Without financial difficulty | Education | Parents unable to model values in person; possible long-term impact |
| Without financial difficulty | Emotion | Absent parents may not notice a child's emotional distress — risk of unaddressed psychological issues |
| With financial difficulty | Time / companionship | No companion for extended periods (1–2 years) |
| With financial difficulty | Security | Children living with grandparents may be more vulnerable (e.g. kidnapping risk) due to reduced monitoring capacity |
| With financial difficulty | Education | Both formal education access and value-shaping affected; rural education quality flagged as a factor |

Important: the sheets also captured early "possible solutions" (babysitter/volunteer apps, tutors, summer camps, security talks, donation schemes, volunteer teachers). Per the course's own pacing, none of these should be treated as decided — a design concept isn't expected until Week 5, and should come from data, not from this initial brainstorm. Carry them forward only as candidate hypotheses to test, not commitments.

New assumption to test in Research Cycle 1a/1b: "Financial difficulty status is the right variable to segment this population by, and meaningfully changes the problem profile." This wasn't in the original Who/How/Why/Impact/Risks framing and should be explicitly checked against literature and interview data — it's plausible, but currently based on team intuition rather than evidence.

## Research Cycle 1a — Framing (Week 3)

| Task | Output | Owner | Target |
| --- | --- | --- | --- |
| Finalise Who / How / Why / Impact / Risks framing, incorporating the financial-difficulty segmentation above | Structured doc in Miro | Whole team | Week 3 |
| Literature scan on left-behind children — specifically look for evidence on whether financial status changes outcomes | Annotated bibliography, 8–10 sources min | 2 members | Week 3 |
| Draft assumptions to test (e.g. "experience is uniform across ages," "financial difficulty is the key segmenting variable") | List of assumptions | Whole team | Week 3 |
| Method selection for Week 3 topic — pick at least 2 complementary methods so findings can be triangulated | Method shortlist + rationale | Whole team | Week 3 |

## Research Cycle 1b — Grounding & Synthesis (Week 4)

| Task | Output | Owner | Target |
| --- | --- | --- | --- |
| Pilot the selected methods with 1–2 participants (a small first pass, not the full data collection) — e.g. one informal interview, one quick look at an online forum | Pilot notes | 1–2 members | Week 4 |
| Ethics & values pass (Week 4 topic: vulnerable population) — revisit before and after the pilot | Ethics considerations draft | Whole team | Week 4 |
| Synthesis session: cross-check the pilot and literature findings against the Week 3 assumptions | Updated framing + revised assumptions | Whole team | Week 4 |

Gate before moving to Phase 2: the team (and each member individually, since Assessment 1 is individual) should be able to state the problem, its stakeholders, and its ethical risks clearly, backed by at least two independent sources of evidence — without naming a solution. This is now formalised as a Problem Identification Document — a single reviewable file consolidating the Who/How/Why/Impact/Risks framing, the Week 3 financial-difficulty segmentation, and a living Assumptions Register marking every claim as untested/tested/confirmed. Phase 2 doesn't start in earnest until this document exists in reviewable form. If Cycle 1b synthesis surfaces a significantly different picture than Cycle 1a assumed, revise the framing before moving on.

# Phase 2 — Knowledge Gathering

Weeks 4–5 (20/08, 27/08/26)

Deepens and completes the research set in motion in Phase 1: executing the full Suite of Methods the team agreed on in Week 3, before any synthesis or design thinking begins. This phase is about building the team's shared evidence base — not about writing anything for submission. Phase 2 starts from the Problem Identification Document produced at the end of Phase 1, and its central job is to work through that document's Assumptions Register, testing each row against real evidence.

| Task | Output | Owner | Target |
| --- | --- | --- | --- |
| Complete literature review — extend the Phase 1 scan into a fuller annotated bibliography | Annotated bibliography (8–10+ sources) | 2 members (rotating/expanding) | Week 4 |
| Formulate question guides for each assigned method (Contextual Inquiry, Rapid Ethnography, Digital Ethnography, Mapping, Object Inventory), informed by what the Week 4 pilot surfaced | Method-specific question/prompt guides | Each member, for their assigned method | Week 4 |
| Conduct the full round of interviews / observations / mapping sessions / object inventories (beyond the Week 4 pilot) — each member engages at least one participant; team-wide target 6–10 participants | Transcripts, observation logs, maps, object inventories | Each member | Week 4–5 |
| Digital ethnography: notify gatekeeper/community first, then observe/participate per ethical conduct expectations | Digital ethnography log | Assigned member(s) | Week 4–5 |
| Qualitative data analysis (Week 5 studio topic) — code all data against Who/How/Why/Impact/Risks, the financial-difficulty segmentation, and an "unexpected" category | Coded findings | Whole team | Week 5 |
| Team synthesis session — test the "financial difficulty is the key segmenting variable" assumption against what the data shows | Synthesised findings + updated framing | Whole team | Week 5 |
| Design concept hypothesis — the formal Week 3–5 output Assessment 2 grades; a shared direction, not a specification | Design concept hypothesis | Whole team | Week 5 |

Not a phase — Assessment 1 (Individual Proposal): Assessment 1 (~1500 words, due 07/09/26, 3pm) isn't a separate stage of the project. It's an individual deliverable each member writes by drawing on the shared knowledge base built across Phases 1–2 — their own take on the problem, desired interactions, and ethical issues. It happens in parallel with Phase 3's early team prototyping, not before or after it as its own gate.

# Phase 3 — Iteration 1 (Team)

Weeks 6–8 (03/09, 10/09, 17/09/26) — Design Exhibit 1 (Milestone 1, 10%), due 17/09/26

- Prototyping methods, API & tangibles (Week 6, 03/09/26)

- UX design (Week 7, 10/09/26)

- Deliverable: work-in-progress prototype with some interactivity — no user evaluation expected yet

- The exhibit is a checkpoint for showing real progress, not the target itself — the sub-cycles below are what actually produce something worth showing

- Draws on Phase 2's synthesised findings and design concept hypothesis, plus each member's individual Assessment 1 proposal (due 07/09/26) as they come in — Assessment 1 sits inside this window, not before it

Treat this as three short internal loops rather than one build:

| Sub-cycle | Task | Target |
| --- | --- | --- |
| 3.1 Converge | Reconcile individual Assessment 1 proposals with the Phase 2 design concept hypothesis into one team direction; note what's being dropped and why | Week 6 (03/09) |
| 3.2 Sketch → critique | Produce 2–3 rough concept sketches/paper prototypes, critique as a team against the Phase 1–2 research findings, pick one | Week 6–7 (03–10/09) |
| 3.3 Build → internal test | Build low/mid-fidelity interactive prototype; do a quick internal walkthrough (team members act as users) and fix obvious breakages before the exhibit | Week 7–8 (10–17/09) |
| — | Prepare exhibit boards/materials | Week 8 (17/09) |
| — | Design Exhibit 1 | 17/09/26 |

Keep a short note of what changed between 3.1 → 3.2 → 3.3 — this is exactly the kind of evidence Assessment 3 (design journal interview) asks for.

# Phase 4 — User Enactment & Evaluation

Week 9 (24/09/26) + Semester Break + Weeks 10–11 (08/10, 15/10/26)

- Week 9: Wizard of Oz, role playing, bodystorming, simulated environments

- Semester break falls immediately after Week 9 — a natural pause between generating enactment insights and running formal evaluation

- Weeks 10–11 (post-break): evaluation methods, field trial methods

This phase is where research and design iteration should be tightest — use it to generate real evidence for Phase 5, not just to tick off the studio activity.

| Task | Output | Target |
| --- | --- | --- |
| Design and run user enactment activity (Wizard of Oz / role play / bodystorming) on the Exhibit 1 prototype | Enactment notes, video/photo evidence | Week 9 (24/09) |
| Analyse enactment findings — what broke, what surprised the team, what to change | Revised prototype backlog | Week 9–10 |
| Plan evaluation approach: define what you're testing (usability? emotional impact?) and pick methods accordingly | Evaluation plan | Week 10 (08/10) |
| Conduct field trial with prototype, ideally 2+ rounds (test → tweak → retest) rather than one-shot | Field trial data + iteration log | Week 11 (15/10) |
| Synthesis: consolidate findings into concrete design changes for Phase 5 | Prioritised change list | Week 11 |

# Phase 5 — Iteration 2 (Team)

Weeks 12–13 (22/10, 29/10/26) — Design Exhibit 2 (Milestone 2, 25%), due 29/10/26

- Week 12's official studio topic is "Prep for Exhibit" — treat this as the main build/refinement week, not just logistics

- High-fidelity prototype, polished aesthetics/interactions

- Must integrate findings from user engagement/testing (Phase 4)

- Again, the exhibit is where progress gets shown — the refinement work in the table below is what matters

| Task | Target |
| --- | --- |
| Refine prototype using field trial insights | Week 12 (22/10) |
| Prep exhibit boards/materials | Week 12 (22/10) |
| Design Exhibit 2 | 29/10/26 |

# Phase 6 — Wrap-up

Weeks 14–16

| Week | Studio Topic | Item | Due |
| --- | --- | --- | --- |
| 14 | SWOT VAC (no scheduled studio) | Use as buffer/writing time for the report | — |
| 15 | Assessment 2: Milestone 3 | Project Report (~3000 words) | 13/11/26, 3pm |
| 15 | — | Assessment 3 — Individual interview (based on design journal, min. 9 entries) | 9–13/11/26 |
| 16 | — | Assessment 4 (PG only) — Interaction Design Review | 16/11/26, 3pm |

# Ongoing Throughout

Design journal: at least 1 entry/week in Miro, min. 9 over 12 weeks (description + visual evidence + learning statement). This directly feeds Assessment 3 — treat it as a running log from Phase 1 onward, not something to backfill later.

Teaching team check-ins: weekly studio feedback on journal entries.

Note: Phase 1 (where the team currently is) is deliberately solution-free per the course's own structure — "desired interactions" only enters the brief at Assessment 1. Keep Miro brainstorming and problem-framing docs focused on Who/How/Why/Impact/Risks until that point.